## RAW DATA
Project ID | Project Name | Project Type | Location | Start Date | End Date | Project Status | Priority | Task ID | Task Name | Task Status | Assigned To | Hours Spent | Progress | Budget | Actual Cost | Buget Utilization
P001 | Renovation of a School Project 001 | Renovation | Texas | 2024-07-21 | 2024-08-08 | Behind | Medium | T001 | Task 001 of Renovation of a School Project 001 | In Progress | Bob | 12 | 0.24 | 9621 | 0 | 0
P001 | Renovation of a School Project 001 | Renovation | New Jersey | 2024-07-21 | 2024-08-12 | Behind | High | T002 | Task 002 of Renovation of a School Project 001 | In Progress | Charlie | 4 | 0.56 | 7814 | 0 | 0
P001 | Renovation of a School Project 001 | Renovation | Ohio | 2024-07-21 | 2024-08-10 | Behind | High | T003 | Task 003 of Renovation of a School Project 001 | Completed | Charlie | 5 | 1 | 1028 | 1011 | 0.98346
P002 | Innovation of a Classroom Project 002 | Innovation | Pennsylvania | 2024-06-04 | 2025-07-12 | On Track | High | T001 | Task 001 of Innovation of a Classroom Project 002 | Pending | Charlie | 24 | 0.33 | 1530 | 0 | 0
P002 | Innovation of a Classroom Project 002 | Innovation | New York | 2024-06-04 | 2025-06-26 | On Track | Medium | T002 | Task 002 of Innovation of a Classroom Project 002 | Pending | Charlie | 26 | 0.32 | 7201 | 0 | 0
P002 | Innovation of a Classroom Project 002 | Innovation | California | 2024-06-04 | 2025-03-25 | On Track | Low | T003 | Task 003 of Innovation of a Classroom Project 002 | In Progress | Alice | 28 | 0.29 | 9814 | 0 | 0
P003 | Construction of a Hospital Wing Project 003 | Construction | Pennsylvania | 2024-07-20 | 2024-08-22 | Completed | Low | T001 | Task 001 of Construction of a Hospital Wing Project 003 | Completed | Grace | 7 | 1 | 7981 | 7717 | 0.96692
P003 | Construction of a Hospital Wing Project 003 | Construction | Virginia | 2024-07-20 | 2024-09-25 | Completed | Medium | T002 | Task 002 of Construction of a Hospital Wing Project 003 | Completed | Frank | 23 | 1 | 1032 | 637 | 0.61725
P003 | Construction of a Hospital Wing Project 003 | Construction | Ohio | 2024-07-20 | 2024-08-22 | Completed | Medium | T003 | Task 003 of Construction of a Hospital Wing Project 003 | Completed | Grace | 13 | 1 | 8546 | 8502 | 0.99485
P004 | Road Expansion Project 004 | Infrastructure | Pennsylvania | 2024-04-25 | 2024-05-06 | Completed | Medium | T001 | Task 001 of Road Expansion Project 004 | Completed | Frank | 28 | 1 | 3728 | 3369 | 0.9037
P004 | Road Expansion Project 004 | Infrastructure | Texas | 2024-04-25 | 2024-05-05 | Completed | High | T002 | Task 002 of Road Expansion Project 004 | In Progress | Charlie | 26 | 0.99 | 9707 | 0 | 0
P004 | Road Expansion Project 004 | Infrastructure | Texas | 2024-04-25 | 2024-05-10 | Completed | Medium | T003 | Task 003 of Road Expansion Project 004 | Pending | Charlie | 18 | 0.74 | 5712 | 0 | 0
P005 | Bridge Maintenance Project 005 | Maintenance | Michigan | 2024-06-30 | 2025-07-31 | Behind | Medium | T001 | Task 001 of Bridge Maintenance Project 005 | Pending | Charlie | 18 | 0.78 | 3453 | 0 | 0
P005 | Bridge Maintenance Project 005 | Maintenance | California | 2024-06-30 | 2024-08-02 | Behind | Medium | T002 | Task 002 of Bridge Maintenance Project 005 | Completed | Frank | 7 | 1 | 2896 | 2643 | 0.91264
P005 | Bridge Maintenance Project 005 | Maintenance | Virginia | 2024-06-30 | 2025-06-30 | Behind | High | T003 | Task 003 of Bridge Maintenance Project 005 | Pending | Grace | 0 | 0.04 | 6463 | 0 | 0
P006 | Office Building Renovation Project 006 | Renovation | Michigan | 2024-08-09 | 2024-09-11 | Behind | Low | T001 | Task 001 of Office Building Renovation Project 006 | Completed | Alice | 9 | 1 | 3206 | 2739 | 0.85434
P006 | Office Building Renovation Project 006 | Renovation | North Carolina | 2024-08-09 | 2024-09-11 | Behind | Medium | T002 | Task 002 of Office Building Renovation Project 006 | Completed | Frank | 40 | 1 | 6477 | 6402 | 0.98842
P006 | Office Building Renovation Project 006 | Renovation | Pennsylvania | 2024-08-09 | 2025-02-20 | Behind | High | T003 | Task 003 of Office Building Renovation Project 006 | In Progress | Charlie | 40 | 0.07 | 8634 | 0 | 0
P007 | Apartment Complex Development Project 007 | Other | California | 2024-08-06 | 2024-11-17 | On Track | High | T001 | Task 001 of Apartment Complex Development Project 007 | Pending | Ivy | 32 | 0.62 | 2552 | 0 | 0
P007 | Apartment Complex Development Project 007 | Other | Florida | 2024-08-06 | 2024-11-29 | On Track | Medium | T002 | Task 002 of Apartment Complex Development Project 007 | Pending | Grace | 25 | 0.85 | 4699 | 0 | 0
P007 | Apartment Complex Development Project 007 | Other | Pennsylvania | 2024-08-06 | 2024-11-17 | On Track | Low | T003 | Task 003 of Apartment Complex Development Project 007 | Pending | Ivy | 10 | 0.92 | 1720 | 0 | 0
P008 | Commercial Center Construction Project 008 | Construction | Illinois | 2024-04-17 | 2024-09-13 | On Track | Medium | T001 | Task 001 of Commercial Center Construction Project 008 | Pending | Alice | 17 | 0.59 | 9458 | 0 | 0
P008 | Commercial Center Construction Project 008 | Construction | Washington | 2024-04-17 | 2024-11-05 | On Track | Low | T002 | Task 002 of Commercial Center Construction Project 008 | Pending | Charlie | 21 | 0.26 | 4735 | 0 | 0
P008 | Commercial Center Construction Project 008 | Construction | Georgia | 2024-04-17 | 2024-10-19 | On Track | High | T003 | Task 003 of Commercial Center Construction Project 008 | Pending | Charlie | 7 | 0.45 | 9460 | 0 | 0
P009 | Highway Reconstruction Project 009 | Other | Texas | 2024-04-27 | 2025-04-28 | On Hold | High | T001 | Task 001 of Highway Reconstruction Project 009 | Pending | Charlie | 35 | 0.36 | 6385 | 0 | 0
P009 | Highway Reconstruction Project 009 | Other | Virginia | 2024-04-27 | 2025-06-01 | On Hold | Medium | T002 | Task 002 of Highway Reconstruction Project 009 | Pending | Ivy | 2 | 0.88 | 7980 | 0 | 0
P009 | Highway Reconstruction Project 009 | Other | Ohio | 2024-04-27 | 2025-05-26 | On Hold | Low | T003 | Task 003 of Highway Reconstruction Project 009 | Pending | Charlie | 26 | 0.97 | 1106 | 0 | 0
P010 | Airport Expansion Project 010 | Other | New Jersey | 2024-02-14 | 2024-06-15 | On Track | High | T001 | Task 001 of Airport Expansion Project 010 | Pending | Grace | 32 | 0.1 | 1577 | 4850 | 3.0755
P010 | Airport Expansion Project 010 | Other | Ohio | 2024-02-14 | 2024-06-08 | On Track | High | T002 | Task 002 of Airport Expansion Project 010 | Pending | Alice | 16 | 0.7 | 3110 | 0 | 0
P010 | Airport Expansion Project 010 | Other | Ohio | 2024-02-14 | 2024-05-26 | On Track | Low | T003 | Task 003 of Airport Expansion Project 010 | Pending | Charlie | 11 | 0.6 | 3432 | 0 | 0
P011 | Shopping Mall Renovation Project 011 | Renovation | Texas | 2024-05-08 | 2024-07-28 | Completed | High | T001 | Task 001 of Shopping Mall Renovation Project 011 | In Progress | Eve | 15 | 0.64 | 3544 | 0 | 0
P011 | Shopping Mall Renovation Project 011 | Renovation | Georgia | 2024-05-08 | 2024-08-19 | Completed | High | T002 | Task 002 of Shopping Mall Renovation Project 011 | In Progress | Eve | 40 | 0.44 | 7808 | 0 | 0
P011 | Shopping Mall Renovation Project 011 | Renovation | Florida | 2024-05-08 | 2024-08-01 | Completed | High | T003 | Task 003 of Shopping Mall Renovation Project 011 | Pending | Alice | 1 | 0.02 | 1776 | 0 | 0
P012 | University Dormitory Construction Project 012 | Construction | Georgia | 2024-01-27 | 2024-02-29 | Completed | High | T001 | Task 001 of University Dormitory Construction Project 012 | Completed | Frank | 15 | 1 | 1815 | 1679 | 0.92507
P012 | University Dormitory Construction Project 012 | Construction | Ohio | 2024-01-27 | 2024-02-29 | Completed | High | T002 | Task 002 of University Dormitory Construction Project 012 | Completed | Bob | 40 | 1 | 8915 | 8464 | 0.94941
P012 | University Dormitory Construction Project 012 | Construction | New York | 2024-01-27 | 2025-06-27 | Completed | Medium | T003 | Task 003 of University Dormitory Construction Project 012 | Pending | Alice | 18 | 0.98 | 9242 | 0 | 0
P013 | Sports Stadium Upgrade Project 013 | Other | Florida | 2024-02-09 | 2024-08-24 | On Hold | Medium | T001 | Task 001 of Sports Stadium Upgrade Project 013 | Completed | Alice | 12 | 1 | 9559 | 9379 | 0.98117
P013 | Sports Stadium Upgrade Project 013 | Other | Michigan | 2024-02-09 | 2024-07-06 | On Hold | Medium | T002 | Task 002 of Sports Stadium Upgrade Project 013 | In Progress | Bob | 38 | 0.28 | 4795 | 0 | 0
P013 | Sports Stadium Upgrade Project 013 | Other | California | 2024-02-09 | 2024-07-28 | On Hold | Medium | T003 | Task 003 of Sports Stadium Upgrade Project 013 | In Progress | Alice | 6 | 0.55 | 5258 | 0 | 0
P014 | Public Library Renovation Project 014 | Renovation | Ohio | 2024-07-30 | 2024-12-20 | Behind | Low | T001 | Task 001 of Public Library Renovation Project 014 | In Progress | Grace | 31 | 0.1 | 8531 | 0 | 0
P014 | Public Library Renovation Project 014 | Renovation | Ohio | 2024-07-30 | 2025-01-30 | Behind | Low | T002 | Task 002 of Public Library Renovation Project 014 | Pending | Charlie | 8 | 0.82 | 3564 | 0 | 0
P014 | Public Library Renovation Project 014 | Renovation | New Jersey | 2024-07-30 | 2024-12-29 | Behind | Medium | T003 | Task 003 of Public Library Renovation Project 014 | Pending | Charlie | 6 | 0.22 | 6213 | 0 | 0
P015 | Building a Park Project 015 | Other | Georgia | 2024-03-17 | 2024-04-19 | On Hold | High | T001 | Task 001 of Building a Park Project 015 | Completed | Ivy | 8 | 1 | 4714 | 4608 | 0.97751
P015 | Building a Park Project 015 | Other | New Jersey | 2024-03-17 | 2024-04-19 | On Hold | Medium | T002 | Task 002 of Building a Park Project 015 | Completed | Charlie | 4 | 1 | 1026 | 528 | 0.51462
P015 | Building a Park Project 015 | Other | North Carolina | 2024-03-17 | 2024-04-19 | On Hold | High | T003 | Task 003 of Building a Park Project 015 | Completed | Bob | 22 | 1 | 5365 | 5232 | 0.97521
P016 | Renovation of a School Project 016 | Renovation | Georgia | 2024-02-18 | 2024-09-25 | Completed | Medium | T001 | Task 001 of Renovation of a School Project 016 | Completed | Bob | 5 | 1 | 3688 | 3610 | 0.97885
P016 | Renovation of a School Project 016 | Renovation | Texas | 2024-02-18 | 2024-10-22 | Completed | High | T002 | Task 002 of Renovation of a School Project 016 | Pending | Eve | 27 | 0.38 | 3233 | 0 | 0
P016 | Renovation of a School Project 016 | Renovation | Florida | 2024-02-18 | 2024-09-15 | Completed | Medium | T003 | Task 003 of Renovation of a School Project 016 | Pending | Eve | 25 | 0.55 | 8366 | 0 | 0
P017 | Innovation of a Classroom Project 017 | Innovation | Virginia | 2024-04-02 | 2024-10-25 | On Track | Low | T001 | Task 001 of Innovation of a Classroom Project 017 | Pending | Eve | 40 | 0.87 | 1856 | 0 | 0
P017 | Innovation of a Classroom Project 017 | Innovation | Illinois | 2024-04-02 | 2024-09-23 | On Track | High | T002 | Task 002 of Innovation of a Classroom Project 017 | Completed | Charlie | 34 | 1 | 5620 | 5481 | 0.97527
P017 | Innovation of a Classroom Project 017 | Innovation | Georgia | 2024-04-02 | 2024-10-14 | On Track | High | T003 | Task 003 of Innovation of a Classroom Project 017 | In Progress | Alice | 18 | 0.62 | 1904 | 0 | 0
P018 | Construction of a Hospital Wing Project 018 | Construction | Ohio | 2024-02-09 | 2024-03-05 | Behind | Medium | T001 | Task 001 of Construction of a Hospital Wing Project 018 | In Progress | Grace | 26 | 0.66 | 5908 | 0 | 0
P018 | Construction of a Hospital Wing Project 018 | Construction | North Carolina | 2024-02-09 | 2024-03-01 | Behind | Medium | T002 | Task 002 of Construction of a Hospital Wing Project 018 | In Progress | Grace | 37 | 0.54 | 2176 | 0 | 0
P018 | Construction of a Hospital Wing Project 018 | Construction | Pennsylvania | 2024-02-09 | 2024-02-25 | Behind | Medium | T003 | Task 003 of Construction of a Hospital Wing Project 018 | Pending | Grace | 7 | 0.2 | 9002 | 0 | 0
P019 | Road Expansion Project 019 | Infrastructure | Texas | 2024-06-10 | 2024-12-30 | Behind | High | T001 | Task 001 of Road Expansion Project 019 | Pending | Grace | 11 | 0.61 | 6821 | 0 | 0
P019 | Road Expansion Project 019 | Infrastructure | Ohio | 2024-06-10 | 2024-09-25 | Behind | Medium | T002 | Task 002 of Road Expansion Project 019 | Completed | Ivy | 1 | 1 | 7324 | 7263 | 0.99167
P019 | Road Expansion Project 019 | Infrastructure | Georgia | 2024-06-10 | 2024-12-24 | Behind | Medium | T003 | Task 003 of Road Expansion Project 019 | Pending | Charlie | 13 | 0.46 | 3099 | 0 | 0
P020 | Bridge Maintenance Project 020 | Maintenance | Michigan | 2024-04-10 | 2024-07-03 | Completed | Medium | T001 | Task 001 of Bridge Maintenance Project 020 | Completed | Eve | 18 | 1 | 7962 | 7526 | 0.94524
P020 | Bridge Maintenance Project 020 | Maintenance | California | 2024-04-10 | 2024-08-02 | Completed | High | T002 | Task 002 of Bridge Maintenance Project 020 | In Progress | Grace | 36 | 0.84 | 7221 | 0 | 0
P020 | Bridge Maintenance Project 020 | Maintenance | Michigan | 2024-04-10 | 2024-07-02 | Completed | High | T003 | Task 003 of Bridge Maintenance Project 020 | Pending | Grace | 24 | 0.11 | 7256 | 0 | 0
P021 | Office Building Renovation Project 021 | Renovation | North Carolina | 2024-03-21 | 2024-12-15 | Behind | High | T001 | Task 001 of Office Building Renovation Project 021 | In Progress | Alice | 26 | 0.43 | 8483 | 0 | 0
P021 | Office Building Renovation Project 021 | Renovation | Michigan | 2024-03-21 | 2024-09-25 | Behind | High | T002 | Task 002 of Office Building Renovation Project 021 | Completed | Frank | 21 | 1 | 2463 | 2091 | 0.84896
P021 | Office Building Renovation Project 021 | Renovation | Georgia | 2024-03-21 | 2024-09-20 | Behind | High | T003 | Task 003 of Office Building Renovation Project 021 | Completed | Ivy | 15 | 1 | 8372 | 7940 | 0.9484
P022 | Apartment Complex Development Project 022 | Other | Michigan | 2024-01-09 | 2024-04-11 | On Track | High | T001 | Task 001 of Apartment Complex Development Project 022 | In Progress | Ivy | 6 | 0.68 | 8903 | 0 | 0
P022 | Apartment Complex Development Project 022 | Other | California | 2024-01-09 | 2024-04-28 | On Track | Medium | T002 | Task 002 of Apartment Complex Development Project 022 | In Progress | Grace | 7 | 0.28 | 1255 | 0 | 0
P022 | Apartment Complex Development Project 022 | Other | Virginia | 2024-01-09 | 2024-04-24 | On Track | High | T003 | Task 003 of Apartment Complex Development Project 022 | In Progress | Ivy | 18 | 0.77 | 1424 | 2183 | 1.533
P023 | Commercial Center Construction Project 023 | Construction | Virginia | 2024-01-04 | 2024-05-18 | Behind | High | T001 | Task 001 of Commercial Center Construction Project 023 | Pending | Alice | 17 | 0.45 | 3662 | 0 | 0
P023 | Commercial Center Construction Project 023 | Construction | North Carolina | 2024-01-04 | 2024-06-01 | Behind | Medium | T002 | Task 002 of Commercial Center Construction Project 023 | Pending | Charlie | 27 | 0.02 | 2437 | 0 | 0
P023 | Commercial Center Construction Project 023 | Construction | Illinois | 2024-01-04 | 2024-04-10 | Behind | Low | T003 | Task 003 of Commercial Center Construction Project 023 | In Progress | Charlie | 19 | 0.45 | 7519 | 0 | 0
P024 | Highway Reconstruction Project 024 | Other | Illinois | 2024-08-16 | 2024-08-29 | Completed | Medium | T001 | Task 001 of Highway Reconstruction Project 024 | In Progress | Charlie | 1 | 0.05 | 5955 | 0 | 0
P024 | Highway Reconstruction Project 024 | Other | Florida | 2024-08-16 | 2024-09-04 | Completed | Low | T002 | Task 002 of Highway Reconstruction Project 024 | Pending | Ivy | 1 | 0.75 | 1799 | 0 | 0
P024 | Highway Reconstruction Project 024 | Other | Michigan | 2024-08-16 | 2024-09-01 | Completed | Medium | T003 | Task 003 of Highway Reconstruction Project 024 | Completed | Eve | 24 | 1 | 8925 | 8659 | 0.9702
P025 | Airport Expansion Project 025 | Other | Washington | 2024-05-05 | 2024-07-20 | On Hold | High | T001 | Task 001 of Airport Expansion Project 025 | Completed | Alice | 37 | 1 | 8938 | 8487 | 0.94954
P025 | Airport Expansion Project 025 | Other | New Jersey | 2024-05-05 | 2024-07-17 | On Hold | Low | T002 | Task 002 of Airport Expansion Project 025 | In Progress | David | 10 | 0.72 | 8533 | 0 | 0
P025 | Airport Expansion Project 025 | Other | New York | 2024-05-05 | 2024-07-03 | On Hold | Medium | T003 | Task 003 of Airport Expansion Project 025 | In Progress | Charlie | 16 | 0.5 | 8402 | 0 | 0
P026 | Shopping Mall Renovation Project 026 | Renovation | Pennsylvania | 2024-07-08 | 2025-04-30 | On Hold | Low | T001 | Task 001 of Shopping Mall Renovation Project 026 | In Progress | Eve | 21 | 0.1 | 6524 | 0 | 0
P026 | Shopping Mall Renovation Project 026 | Renovation | Illinois | 2024-07-08 | 2024-08-10 | On Hold | Medium | T002 | Task 002 of Shopping Mall Renovation Project 026 | Completed | Eve | 34 | 1 | 8061 | 8002 | 0.99268
P026 | Shopping Mall Renovation Project 026 | Renovation | Georgia | 2024-07-08 | 2025-04-06 | On Hold | High | T003 | Task 003 of Shopping Mall Renovation Project 026 | Pending | Alice | 3 | 0.82 | 2436 | 0 | 0
P027 | University Dormitory Construction Project 027 | Construction | Michigan | 2024-01-03 | 2024-12-28 | Completed | High | T001 | Task 001 of University Dormitory Construction Project 027 | In Progress | Frank | 35 | 0.84 | 9670 | 0 | 0
P027 | University Dormitory Construction Project 027 | Construction | Washington | 2024-01-03 | 2025-03-22 | Completed | Low | T002 | Task 002 of University Dormitory Construction Project 027 | In Progress | Bob | 7 | 1 | 1646 | 4190 | 2.5456
P027 | University Dormitory Construction Project 027 | Construction | Ohio | 2024-01-03 | 2025-01-19 | Completed | Medium | T003 | Task 003 of University Dormitory Construction Project 027 | In Progress | Alice | 30 | 0.19 | 3853 | 0 | 0
P028 | Sports Stadium Upgrade Project 028 | Other | California | 2024-07-25 | 2025-01-19 | Behind | Medium | T001 | Task 001 of Sports Stadium Upgrade Project 028 | Pending | Alice | 22 | 0.31 | 5266 | 0 | 0
P028 | Sports Stadium Upgrade Project 028 | Other | California | 2024-07-25 | 2025-05-28 | Behind | Medium | T002 | Task 002 of Sports Stadium Upgrade Project 028 | Pending | Bob | 16 | 0.78 | 4878 | 0 | 0
P028 | Sports Stadium Upgrade Project 028 | Other | New York | 2024-07-25 | 2025-01-16 | Behind | Low | T003 | Task 003 of Sports Stadium Upgrade Project 028 | Pending | David | 23 | 0.98 | 4589 | 0 | 0
P029 | Public Library Renovation Project 029 | Renovation | North Carolina | 2024-04-10 | 2024-05-13 | On Track | Low | T001 | Task 001 of Public Library Renovation Project 029 | Completed | Grace | 33 | 1 | 3498 | 3235 | 0.92481
P029 | Public Library Renovation Project 029 | Renovation | Michigan | 2024-04-10 | 2024-12-21 | On Track | High | T002 | Task 002 of Public Library Renovation Project 029 | Pending | Charlie | 30 | 0.15 | 7342 | 0 | 0
P029 | Public Library Renovation Project 029 | Renovation | Virginia | 2024-04-10 | 2025-01-23 | On Track | High | T003 | Task 003 of Public Library Renovation Project 029 | Pending | Charlie | 22 | 0.4 | 3172 | 0 | 0
P030 | Building a Park Project 030 | Other | Washington | 2024-07-16 | 2024-07-29 | On Track | High | T001 | Task 001 of Building a Park Project 030 | Pending | Ivy | 33 | 0.79 | 8742 | 0 | 0
P030 | Building a Park Project 030 | Other | Pennsylvania | 2024-07-16 | 2024-07-29 | On Track | High | T002 | Task 002 of Building a Park Project 030 | Pending | Charlie | 1 | 0.28 | 4274 | 0 | 0
P030 | Building a Park Project 030 | Other | New York | 2024-07-16 | 2024-07-29 | On Track | High | T003 | Task 003 of Building a Park Project 030 | In Progress | Bob | 16 | 0.07 | 3338 | 0 | 0
P031 | Renovation of a School Project 031 | Renovation | Illinois | 2024-03-19 | 2024-06-09 | On Track | High | T001 | Task 001 of Renovation of a School Project 031 | In Progress | Bob | 2 | 0.45 | 3147 | 0 | 0
P031 | Renovation of a School Project 031 | Renovation | Georgia | 2024-03-19 | 2024-06-06 | On Track | High | T002 | Task 002 of Renovation of a School Project 031 | In Progress | Eve | 11 | 0.79 | 8355 | 0 | 0
P031 | Renovation of a School Project 031 | Renovation | Georgia | 2024-03-19 | 2024-06-03 | On Track | Medium | T003 | Task 003 of Renovation of a School Project 031 | Completed | Eve | 5 | 1 | 4000 | 3595 | 0.89875
P032 | Innovation of a Classroom Project 032 | Innovation | New Jersey | 2024-05-02 | 2025-02-26 | On Hold | High | T001 | Task 001 of Innovation of a Classroom Project 032 | In Progress | Eve | 12 | 0.54 | 4133 | 0 | 0
P032 | Innovation of a Classroom Project 032 | Innovation | New York | 2024-05-02 | 2025-04-16 | On Hold | Medium | T002 | Task 002 of Innovation of a Classroom Project 032 | Pending | Charlie | 4 | 0.39 | 8258 | 0 | 0
P032 | Innovation of a Classroom Project 032 | Innovation | Washington | 2024-05-02 | 2025-03-24 | On Hold | Low | T003 | Task 003 of Innovation of a Classroom Project 032 | In Progress | David | 33 | 0.79 | 3654 | 0 | 0
P033 | Construction of a Hospital Wing Project 033 | Construction | California | 2024-05-15 | 2024-09-25 | Behind | Low | T001 | Task 001 of Construction of a Hospital Wing Project 033 | Completed | David | 4 | 1 | 4561 | 4256 | 0.93313
P033 | Construction of a Hospital Wing Project 033 | Construction | Texas | 2024-05-15 | 2024-10-18 | Behind | High | T002 | Task 002 of Construction of a Hospital Wing Project 033 | In Progress | Grace | 10 | 0.71 | 9743 | 0 | 0
P033 | Construction of a Hospital Wing Project 033 | Construction | New Jersey | 2024-05-15 | 2024-09-23 | Behind | High | T003 | Task 003 of Construction of a Hospital Wing Project 033 | Completed | David | 4 | 1 | 7316 | 7140 | 0.97594
P034 | Road Expansion Project 034 | Infrastructure | Florida | 2024-06-13 | 2024-09-01 | Behind | High | T001 | Task 001 of Road Expansion Project 034 | Pending | Grace | 14 | 0.47 | 2342 | 0 | 0
P034 | Road Expansion Project 034 | Infrastructure | Ohio | 2024-06-13 | 2024-08-17 | Behind | High | T002 | Task 002 of Road Expansion Project 034 | Completed | Ivy | 22 | 1 | 5899 | 5436 | 0.92151
P034 | Road Expansion Project 034 | Infrastructure | Pennsylvania | 2024-06-13 | 2024-08-21 | Behind | High | T003 | Task 003 of Road Expansion Project 034 | In Progress | Charlie | 32 | 0.68 | 8314 | 0 | 0
P035 | Bridge Maintenance Project 035 | Maintenance | New Jersey | 2024-06-28 | 2024-07-31 | On Hold | Medium | T001 | Task 001 of Bridge Maintenance Project 035 | Completed | Eve | 14 | 1 | 7361 | 7026 | 0.95449
P035 | Bridge Maintenance Project 035 | Maintenance | Virginia | 2024-06-28 | 2024-07-31 | On Hold | Low | T002 | Task 002 of Bridge Maintenance Project 035 | Completed | Grace | 11 | 1 | 6901 | 6528 | 0.94595
P035 | Bridge Maintenance Project 035 | Maintenance | New Jersey | 2024-06-28 | 2025-04-26 | On Hold | High | T003 | Task 003 of Bridge Maintenance Project 035 | Pending | David | 40 | 0.29 | 5183 | 0 | 0
P036 | Office Building Renovation Project 036 | Renovation | Michigan | 2024-03-26 | 2024-07-10 | Behind | High | T001 | Task 001 of Office Building Renovation Project 036 | In Progress | Alice | 8 | 0.79 | 1220 | 0 | 0
P036 | Office Building Renovation Project 036 | Renovation | Georgia | 2024-03-26 | 2024-07-29 | Behind | Medium | T002 | Task 002 of Office Building Renovation Project 036 | Pending | Frank | 16 | 0.64 | 6005 | 0 | 0
P036 | Office Building Renovation Project 036 | Renovation | California | 2024-03-26 | 2024-06-28 | Behind | High | T003 | Task 003 of Office Building Renovation Project 036 | Completed | Ivy | 32 | 1 | 3891 | 3841 | 0.98715
P037 | Apartment Complex Development Project 037 | Other | Virginia | 2024-01-16 | 2024-07-31 | Behind | Medium | T001 | Task 001 of Apartment Complex Development Project 037 | In Progress | Ivy | 12 | 0.09 | 9160 | 0 | 0
P037 | Apartment Complex Development Project 037 | Other | Pennsylvania | 2024-01-16 | 2024-05-25 | Behind | High | T002 | Task 002 of Apartment Complex Development Project 037 | Completed | Grace | 15 | 1 | 1719 | 1494 | 0.86911
P037 | Apartment Complex Development Project 037 | Other | Illinois | 2024-01-16 | 2024-06-13 | Behind | High | T003 | Task 003 of Apartment Complex Development Project 037 | Pending | Ivy | 2 | 0.33 | 5180 | 0 | 0
P038 | Commercial Center Construction Project 038 | Construction | Texas | 2024-01-15 | 2024-03-01 | Behind | Medium | T001 | Task 001 of Commercial Center Construction Project 038 | Pending | Alice | 14 | 0.93 | 8804 | 0 | 0
P038 | Commercial Center Construction Project 038 | Construction | Michigan | 2024-01-15 | 2024-03-19 | Behind | Low | T002 | Task 002 of Commercial Center Construction Project 038 | Completed | Charlie | 38 | 1 | 8552 | 8463 | 0.98959
P038 | Commercial Center Construction Project 038 | Construction | Michigan | 2024-01-15 | 2024-03-04 | Behind | High | T003 | Task 003 of Commercial Center Construction Project 038 | In Progress | Charlie | 32 | 0.21 | 6348 | 0 | 0
P039 | Highway Reconstruction Project 039 | Other | Virginia | 2024-01-25 | 2024-03-23 | Completed | High | T001 | Task 001 of Highway Reconstruction Project 039 | Completed | Charlie | 39 | 1 | 5312 | 4818 | 0.907
P039 | Highway Reconstruction Project 039 | Other | Virginia | 2024-01-25 | 2024-03-31 | Completed | High | T002 | Task 002 of Highway Reconstruction Project 039 | Pending | Ivy | 2 | 0.24 | 9232 | 0 | 0
P039 | Highway Reconstruction Project 039 | Other | Michigan | 2024-01-25 | 2024-04-03 | Completed | Medium | T003 | Task 003 of Highway Reconstruction Project 039 | Completed | Eve | 6 | 1 | 3291 | 2824 | 0.8581
P040 | Airport Expansion Project 040 | Other | Florida | 2024-01-26 | 2024-09-25 | Behind | Medium | T001 | Task 001 of Airport Expansion Project 040 | Pending | David | 21 | 0.24 | 4414 | 0 | 0
P040 | Airport Expansion Project 040 | Other | Virginia | 2024-01-26 | 2024-07-29 | Behind | Medium | T002 | Task 002 of Airport Expansion Project 040 | In Progress | David | 21 | 0.29 | 9998 | 0 | 0
P040 | Airport Expansion Project 040 | Other | Michigan | 2024-01-26 | 2024-08-14 | Behind | High | T003 | Task 003 of Airport Expansion Project 040 | Pending | Charlie | 21 | 0.54 | 4869 | 0 | 0
P041 | Shopping Mall Renovation Project 041 | Renovation | Pennsylvania | 2024-03-17 | 2024-03-21 | Completed | High | T001 | Task 001 of Shopping Mall Renovation Project 041 | Completed | Eve | 32 | 1 | 3746 | 3514 | 0.93807
P041 | Shopping Mall Renovation Project 041 | Renovation | Florida | 2024-03-17 | 2024-03-21 | Completed | Medium | T002 | Task 002 of Shopping Mall Renovation Project 041 | Pending | Eve | 30 | 0.93 | 5413 | 0 | 0
P041 | Shopping Mall Renovation Project 041 | Renovation | Georgia | 2024-03-17 | 2024-03-21 | Completed | Medium | T003 | Task 003 of Shopping Mall Renovation Project 041 | In Progress | Alice | 28 | 0.8 | 6416 | 0 | 0
P042 | University Dormitory Construction Project 042 | Construction | North Carolina | 2024-01-31 | 2024-05-29 | Behind | High | T001 | Task 001 of University Dormitory Construction Project 042 | In Progress | Frank | 32 | 0.05 | 5512 | 0 | 0
P042 | University Dormitory Construction Project 042 | Construction | California | 2024-01-31 | 2024-07-30 | Behind | High | T002 | Task 002 of University Dormitory Construction Project 042 | Pending | Bob | 7 | 0.36 | 6632 | 0 | 0
P042 | University Dormitory Construction Project 042 | Construction | New Jersey | 2024-01-31 | 2024-08-02 | Behind | Medium | T003 | Task 003 of University Dormitory Construction Project 042 | Pending | Alice | 29 | 0.66 | 3321 | 0 | 0
P043 | Sports Stadium Upgrade Project 043 | Other | California | 2024-01-05 | 2024-06-02 | On Track | High | T001 | Task 001 of Sports Stadium Upgrade Project 043 | In Progress | Alice | 35 | 0.28 | 9960 | 0 | 0
P043 | Sports Stadium Upgrade Project 043 | Other | Virginia | 2024-01-05 | 2024-05-12 | On Track | High | T002 | Task 002 of Sports Stadium Upgrade Project 043 | Completed | Bob | 6 | 1 | 7019 | 6569 | 0.93589
P043 | Sports Stadium Upgrade Project 043 | Other | North Carolina | 2024-01-05 | 2024-06-23 | On Track | High | T003 | Task 003 of Sports Stadium Upgrade Project 043 | Completed | David | 19 | 1 | 2549 | 2168 | 0.85053
P044 | Public Library Renovation Project 044 | Renovation | Georgia | 2024-04-05 | 2024-07-30 | Behind | High | T001 | Task 001 of Public Library Renovation Project 044 | Pending | Grace | 34 | 0.54 | 4587 | 0 | 0
P044 | Public Library Renovation Project 044 | Renovation | New Jersey | 2024-04-05 | 2024-09-18 | Behind | Low | T002 | Task 002 of Public Library Renovation Project 044 | Completed | Charlie | 8 | 1 | 4629 | 4482 | 0.96824
P044 | Public Library Renovation Project 044 | Renovation | Washington | 2024-04-05 | 2024-09-14 | Behind | High | T003 | Task 003 of Public Library Renovation Project 044 | In Progress | Charlie | 30 | 0.06 | 4113 | 0 | 0
P045 | Building a Park Project 045 | Other | Ohio | 2024-06-11 | 2024-07-14 | Completed | Medium | T001 | Task 001 of Building a Park Project 045 | Completed | Ivy | 25 | 1 | 3423 | 3361 | 0.98189
P045 | Building a Park Project 045 | Other | Texas | 2024-06-11 | 2025-02-25 | Completed | High | T002 | Task 002 of Building a Park Project 045 | In Progress | Charlie | 39 | 0.55 | 2297 | 0 | 0
P045 | Building a Park Project 045 | Other | Virginia | 2024-06-11 | 2024-07-14 | Completed | Low | T003 | Task 003 of Building a Park Project 045 | Completed | Bob | 39 | 1 | 2868 | 2425 | 0.84554
P046 | Renovation of a School Project 046 | Renovation | California | 2024-06-13 | 2024-06-16 | Completed | High | T001 | Task 001 of Renovation of a School Project 046 | In Progress | Bob | 39 | 0.51 | 1771 | 0 | 0
P046 | Renovation of a School Project 046 | Renovation | North Carolina | 2024-06-13 | 2024-06-16 | Completed | Medium | T002 | Task 002 of Renovation of a School Project 046 | Pending | Eve | 25 | 0.43 | 1781 | 0 | 0
P046 | Renovation of a School Project 046 | Renovation | Florida | 2024-06-13 | 2024-06-18 | Completed | High | T003 | Task 003 of Renovation of a School Project 046 | In Progress | Eve | 11 | 0.18 | 7012 | 0 | 0
P047 | Innovation of a Classroom Project 047 | Innovation | Florida | 2024-06-27 | 2024-07-30 | On Hold | High | T001 | Task 001 of Innovation of a Classroom Project 047 | Completed | Eve | 36 | 1 | 2554 | 2262 | 0.88567
P047 | Innovation of a Classroom Project 047 | Innovation | Illinois | 2024-06-27 | 2025-01-09 | On Hold | High | T002 | Task 002 of Innovation of a Classroom Project 047 | In Progress | Charlie | 24 | 0.68 | 8357 | 0 | 0
P047 | Innovation of a Classroom Project 047 | Innovation | Pennsylvania | 2024-06-27 | 2024-09-25 | On Hold | High | T003 | Task 003 of Innovation of a Classroom Project 047 | Completed | David | 18 | 1 | 9034 | 8655 | 0.95805
P048 | Construction of a Hospital Wing Project 048 | Construction | Florida | 2024-06-09 | 2024-12-15 | Completed | High | T001 | Task 001 of Construction of a Hospital Wing Project 048 | In Progress | David | 35 | 0.49 | 5180 | 0 | 0
P048 | Construction of a Hospital Wing Project 048 | Construction | Virginia | 2024-06-09 | 2024-10-31 | Completed | Low | T002 | Task 002 of Construction of a Hospital Wing Project 048 | Pending | Grace | 14 | 0.96 | 5368 | 0 | 0
P048 | Construction of a Hospital Wing Project 048 | Construction | Florida | 2024-06-09 | 2024-11-02 | Completed | Medium | T003 | Task 003 of Construction of a Hospital Wing Project 048 | In Progress | David | 4 | 0.97 | 3812 | 0 | 0
P049 | Road Expansion Project 049 | Infrastructure | Pennsylvania | 2024-07-02 | 2024-08-11 | Completed | Medium | T001 | Task 001 of Road Expansion Project 049 | Completed | Grace | 20 | 1 | 2237 | 2196 | 0.98167
P049 | Road Expansion Project 049 | Infrastructure | Texas | 2024-07-02 | 2024-08-13 | Completed | Low | T002 | Task 002 of Road Expansion Project 049 | Pending | Ivy | 35 | 0.44 | 8742 | 0 | 0
P049 | Road Expansion Project 049 | Infrastructure | New York | 2024-07-02 | 2024-08-23 | Completed | Medium | T003 | Task 003 of Road Expansion Project 049 | Pending | Charlie | 8 | 0.76 | 2613 | 0 | 0
P050 | Bridge Maintenance Project 050 | Maintenance | Illinois | 2024-06-12 | 2024-07-22 | On Track | High | T001 | Task 001 of Bridge Maintenance Project 050 | In Progress | Eve | 38 | 0.71 | 9467 | 0 | 0
P050 | Bridge Maintenance Project 050 | Maintenance | Virginia | 2024-06-12 | 2024-07-25 | On Track | High | T002 | Task 002 of Bridge Maintenance Project 050 | Completed | Grace | 40 | 1 | 1380 | 1005 | 0.72826
P050 | Bridge Maintenance Project 050 | Maintenance | Pennsylvania | 2024-06-12 | 2024-07-31 | On Track | High | T003 | Task 003 of Bridge Maintenance Project 050 | In Progress | David | 18 | 0.09 | 1169 | 0 | 0
P051 | Office Building Renovation Project 051 | Renovation | Ohio | 2024-03-23 | 2024-12-12 | Behind | Low | T001 | Task 001 of Office Building Renovation Project 051 | Pending | Alice | 19 | 0.03 | 7063 | 0 | 0
P051 | Office Building Renovation Project 051 | Renovation | Virginia | 2024-03-23 | 2024-09-25 | Behind | High | T002 | Task 002 of Office Building Renovation Project 051 | Completed | Frank | 27 | 1 | 3221 | 3074 | 0.95436
P051 | Office Building Renovation Project 051 | Renovation | Florida | 2024-03-23 | 2024-10-21 | Behind | High | T003 | Task 003 of Office Building Renovation Project 051 | In Progress | Ivy | 12 | 0.41 | 1201 | 0 | 0
P052 | Apartment Complex Development Project 052 | Other | Virginia | 2024-05-27 | 2025-07-27 | On Hold | Low | T001 | Task 001 of Apartment Complex Development Project 052 | In Progress | Ivy | 19 | 0.88 | 8114 | 9104 | 1.122
P052 | Apartment Complex Development Project 052 | Other | Ohio | 2024-05-27 | 2025-06-11 | On Hold | Low | T002 | Task 002 of Apartment Complex Development Project 052 | Pending | Grace | 14 | 0.19 | 7222 | 0 | 0
P052 | Apartment Complex Development Project 052 | Other | Illinois | 2024-05-27 | 2025-08-22 | On Hold | High | T003 | Task 003 of Apartment Complex Development Project 052 | In Progress | Ivy | 9 | 0.63 | 2022 | 0 | 0
P053 | Commercial Center Construction Project 053 | Construction | Texas | 2024-06-18 | 2024-11-27 | On Track | Low | T001 | Task 001 of Commercial Center Construction Project 053 | In Progress | Alice | 3 | 0.48 | 9700 | 0 | 0
P053 | Commercial Center Construction Project 053 | Construction | New Jersey | 2024-06-18 | 2024-10-21 | On Track | High | T002 | Task 002 of Commercial Center Construction Project 053 | Pending | Charlie | 21 | 0.45 | 7624 | 0 | 0
P053 | Commercial Center Construction Project 053 | Construction | Ohio | 2024-06-18 | 2024-11-07 | On Track | High | T003 | Task 003 of Commercial Center Construction Project 053 | Pending | Charlie | 6 | 0.66 | 9072 | 0 | 0
P054 | Highway Reconstruction Project 054 | Other | New Jersey | 2024-04-15 | 2024-12-26 | Behind | High | T001 | Task 001 of Highway Reconstruction Project 054 | Pending | Charlie | 25 | 0.95 | 6793 | 0 | 0
P054 | Highway Reconstruction Project 054 | Other | California | 2024-04-15 | 2025-03-06 | Behind | High | T002 | Task 002 of Highway Reconstruction Project 054 | Pending | Ivy | 33 | 0.32 | 2398 | 0 | 0
P054 | Highway Reconstruction Project 054 | Other | New York | 2024-04-15 | 2025-04-29 | Behind | Low | T003 | Task 003 of Highway Reconstruction Project 054 | In Progress | Eve | 16 | 0.75 | 9449 | 0 | 0
P055 | Airport Expansion Project 055 | Other | Virginia | 2024-08-28 | 2025-04-21 | On Hold | High | T001 | Task 001 of Airport Expansion Project 055 | In Progress | David | 17 | 0.36 | 8386 | 0 | 0
P055 | Airport Expansion Project 055 | Other | Illinois | 2024-08-28 | 2025-08-28 | On Hold | High | T002 | Task 002 of Airport Expansion Project 055 | Pending | David | 29 | 0.17 | 4294 | 0 | 0
P055 | Airport Expansion Project 055 | Other | Michigan | 2024-08-28 | 2025-09-05 | On Hold | High | T003 | Task 003 of Airport Expansion Project 055 | In Progress | Alice | 27 | 0.09 | 8340 | 0 | 0
P056 | Shopping Mall Renovation Project 056 | Renovation | Pennsylvania | 2024-08-15 | 2024-09-25 | Completed | High | T001 | Task 001 of Shopping Mall Renovation Project 056 | Completed | Eve | 25 | 1 | 3548 | 3528 | 0.99436
P056 | Shopping Mall Renovation Project 056 | Renovation | California | 2024-08-15 | 2024-11-02 | Completed | Low | T002 | Task 002 of Shopping Mall Renovation Project 056 | In Progress | Eve | 23 | 0.08 | 9545 | 0 | 0
P056 | Shopping Mall Renovation Project 056 | Renovation | Florida | 2024-08-15 | 2024-11-04 | Completed | High | T003 | Task 003 of Shopping Mall Renovation Project 056 | In Progress | Alice | 40 | 0.19 | 1449 | 0 | 0
P057 | University Dormitory Construction Project 057 | Construction | North Carolina | 2024-03-23 | 2025-06-15 | On Track | Medium | T001 | Task 001 of University Dormitory Construction Project 057 | In Progress | Frank | 20 | 0.15 | 9728 | 0 | 0
P057 | University Dormitory Construction Project 057 | Construction | New York | 2024-03-23 | 2024-04-25 | On Track | High | T002 | Task 002 of University Dormitory Construction Project 057 | Completed | Bob | 6 | 1 | 6762 | 6621 | 0.97915
P057 | University Dormitory Construction Project 057 | Construction | California | 2024-03-23 | 2024-12-29 | On Track | Low | T003 | Task 003 of University Dormitory Construction Project 057 | In Progress | Alice | 28 | 0.66 | 4093 | 0 | 0
P058 | Sports Stadium Upgrade Project 058 | Other | New Jersey | 2024-07-24 | 2024-08-26 | On Hold | High | T001 | Task 001 of Sports Stadium Upgrade Project 058 | Completed | Alice | 20 | 1 | 9027 | 8655 | 0.95879
P058 | Sports Stadium Upgrade Project 058 | Other | Georgia | 2024-07-24 | 2025-09-04 | On Hold | Low | T002 | Task 002 of Sports Stadium Upgrade Project 058 | Pending | Bob | 10 | 0.99 | 4949 | 0 | 0
P058 | Sports Stadium Upgrade Project 058 | Other | Georgia | 2024-07-24 | 2025-07-06 | On Hold | Low | T003 | Task 003 of Sports Stadium Upgrade Project 058 | Pending | David | 3 | 0.93 | 1671 | 0 | 0
P059 | Public Library Renovation Project 059 | Renovation | North Carolina | 2024-02-08 | 2024-08-31 | On Hold | High | T001 | Task 001 of Public Library Renovation Project 059 | Pending | Grace | 2 | 0.47 | 1634 | 0 | 0
P059 | Public Library Renovation Project 059 | Renovation | Pennsylvania | 2024-02-08 | 2024-07-24 | On Hold | High | T002 | Task 002 of Public Library Renovation Project 059 | Completed | Alice | 34 | 1 | 9178 | 8962 | 0.97647
P059 | Public Library Renovation Project 059 | Renovation | Ohio | 2024-02-08 | 2024-07-13 | On Hold | High | T003 | Task 003 of Public Library Renovation Project 059 | Completed | Charlie | 33 | 1 | 5369 | 4897 | 0.91209
P060 | Building a Park Project 060 | Other | Georgia | 2024-07-04 | 2024-11-16 | On Hold | Medium | T001 | Task 001 of Building a Park Project 060 | Pending | Ivy | 8 | 0.44 | 4383 | 0 | 0
P060 | Building a Park Project 060 | Other | Texas | 2024-07-04 | 2024-09-25 | On Hold | High | T002 | Task 002 of Building a Park Project 060 | Completed | Alice | 5 | 1 | 9106 | 8788 | 0.96508
P060 | Building a Park Project 060 | Other | Washington | 2024-07-04 | 2024-10-26 | On Hold | High | T003 | Task 003 of Building a Park Project 060 | In Progress | Bob | 34 | 0.37 | 7376 | 0 | 0
P061 | Renovation of a School Project 061 | Renovation | Georgia | 2024-06-14 | 2025-05-05 | On Hold | Low | T001 | Task 001 of Renovation of a School Project 061 | Pending | Bob | 31 | 0.84 | 4564 | 0 | 0
P061 | Renovation of a School Project 061 | Renovation | New Jersey | 2024-06-14 | 2025-05-21 | On Hold | Medium | T002 | Task 002 of Renovation of a School Project 061 | In Progress | Eve | 34 | 0.25 | 6685 | 0 | 0
P061 | Renovation of a School Project 061 | Renovation | New Jersey | 2024-06-14 | 2025-09-07 | On Hold | Medium | T003 | Task 003 of Renovation of a School Project 061 | In Progress | Eve | 36 | 0 | 3548 | 0 | 0
P062 | Innovation of a Classroom Project 062 | Innovation | Washington | 2024-07-27 | 2025-03-24 | On Hold | High | T001 | Task 001 of Innovation of a Classroom Project 062 | Pending | Eve | 11 | 0.11 | 5997 | 0 | 0
P062 | Innovation of a Classroom Project 062 | Innovation | New York | 2024-07-27 | 2024-09-25 | On Hold | High | T002 | Task 002 of Innovation of a Classroom Project 062 | Completed | Charlie | 16 | 1 | 3180 | 3081 | 0.96887
P062 | Innovation of a Classroom Project 062 | Innovation | New York | 2024-07-27 | 2025-02-22 | On Hold | High | T003 | Task 003 of Innovation of a Classroom Project 062 | Pending | David | 38 | 0.15 | 2178 | 0 | 0
P063 | Construction of a Hospital Wing Project 063 | Construction | Pennsylvania | 2024-07-16 | 2025-01-07 | On Track | High | T001 | Task 001 of Construction of a Hospital Wing Project 063 | In Progress | David | 5 | 0.55 | 2944 | 0 | 0
P063 | Construction of a Hospital Wing Project 063 | Construction | California | 2024-07-16 | 2024-08-18 | On Track | High | T002 | Task 002 of Construction of a Hospital Wing Project 063 | Completed | Grace | 31 | 1 | 7376 | 6945 | 0.94157
P063 | Construction of a Hospital Wing Project 063 | Construction | Florida | 2024-07-16 | 2025-04-11 | On Track | Low | T003 | Task 003 of Construction of a Hospital Wing Project 063 | In Progress | David | 2 | 0.68 | 6433 | 0 | 0
P064 | Road Expansion Project 064 | Infrastructure | Texas | 2024-06-22 | 2024-09-25 | Behind | Low | T001 | Task 001 of Road Expansion Project 064 | Completed | Grace | 30 | 1 | 5551 | 5315 | 0.95749
P064 | Road Expansion Project 064 | Infrastructure | Illinois | 2024-06-22 | 2024-07-25 | Behind | Medium | T002 | Task 002 of Road Expansion Project 064 | Completed | Ivy | 6 | 1 | 9127 | 8751 | 0.9588
P064 | Road Expansion Project 064 | Infrastructure | Virginia | 2024-06-22 | 2024-09-25 | Behind | High | T003 | Task 003 of Road Expansion Project 064 | Completed | Charlie | 40 | 1 | 9168 | 9025 | 0.9844
P065 | Bridge Maintenance Project 065 | Maintenance | New York | 2024-01-06 | 2024-02-08 | On Track | High | T001 | Task 001 of Bridge Maintenance Project 065 | Completed | Eve | 18 | 1 | 2284 | 2142 | 0.93783
P065 | Bridge Maintenance Project 065 | Maintenance | Florida | 2024-01-06 | 2024-10-25 | On Track | Medium | T002 | Task 002 of Bridge Maintenance Project 065 | In Progress | Grace | 26 | 0.41 | 4973 | 0 | 0
P065 | Bridge Maintenance Project 065 | Maintenance | North Carolina | 2024-01-06 | 2024-09-30 | On Track | High | T003 | Task 003 of Bridge Maintenance Project 065 | Pending | Alice | 26 | 0.6 | 7992 | 0 | 0
P066 | Office Building Renovation Project 066 | Renovation | Georgia | 2024-05-04 | 2024-11-23 | Completed | High | T001 | Task 001 of Office Building Renovation Project 066 | In Progress | Alice | 32 | 0.53 | 3669 | 0 | 0
P066 | Office Building Renovation Project 066 | Renovation | Georgia | 2024-05-04 | 2024-11-06 | Completed | High | T002 | Task 002 of Office Building Renovation Project 066 | Pending | Frank | 20 | 0.55 | 6395 | 0 | 0
P066 | Office Building Renovation Project 066 | Renovation | North Carolina | 2024-05-04 | 2024-09-13 | Completed | Medium | T003 | Task 003 of Office Building Renovation Project 066 | Pending | Ivy | 1 | 0.61 | 4445 | 0 | 0
P067 | Apartment Complex Development Project 067 | Other | Washington | 2024-01-30 | 2025-01-12 | Completed | Low | T001 | Task 001 of Apartment Complex Development Project 067 | In Progress | Ivy | 10 | 0.04 | 1599 | 0 | 0
P067 | Apartment Complex Development Project 067 | Other | Texas | 2024-01-30 | 2024-12-26 | Completed | Medium | T002 | Task 002 of Apartment Complex Development Project 067 | In Progress | Grace | 4 | 0.71 | 9597 | 0 | 0
P067 | Apartment Complex Development Project 067 | Other | New York | 2024-01-30 | 2024-03-03 | Completed | High | T003 | Task 003 of Apartment Complex Development Project 067 | Completed | Ivy | 8 | 1 | 2143 | 1984 | 0.9258
P068 | Commercial Center Construction Project 068 | Construction | New York | 2024-01-30 | 2025-05-28 | Behind | Low | T001 | Task 001 of Commercial Center Construction Project 068 | Pending | Alice | 28 | 0.48 | 6658 | 0 | 0
P068 | Commercial Center Construction Project 068 | Construction | Illinois | 2024-01-30 | 2025-02-13 | Behind | Low | T002 | Task 002 of Commercial Center Construction Project 068 | Pending | Charlie | 32 | 0.93 | 8758 | 0 | 0
P068 | Commercial Center Construction Project 068 | Construction | California | 2024-01-30 | 2024-03-03 | Behind | High | T003 | Task 003 of Commercial Center Construction Project 068 | Completed | Charlie | 8 | 1 | 9806 | 9477 | 0.96645
P069 | Highway Reconstruction Project 069 | Other | Washington | 2024-02-25 | 2025-03-01 | On Track | High | T001 | Task 001 of Highway Reconstruction Project 069 | Pending | Charlie | 16 | 0.28 | 3424 | 0 | 0
P069 | Highway Reconstruction Project 069 | Other | North Carolina | 2024-02-25 | 2025-08-14 | On Track | High | T002 | Task 002 of Highway Reconstruction Project 069 | In Progress | Ivy | 36 | 0.13 | 8166 | 0 | 0
P069 | Highway Reconstruction Project 069 | Other | North Carolina | 2024-02-25 | 2025-08-08 | On Track | Low | T003 | Task 003 of Highway Reconstruction Project 069 | Pending | Eve | 3 | 0.5 | 9968 | 0 | 0
P070 | Airport Expansion Project 070 | Other | California | 2024-02-28 | 2025-06-23 | Behind | High | T001 | Task 001 of Airport Expansion Project 070 | In Progress | Alice | 0 | 0.98 | 9313 | 0 | 0
P070 | Airport Expansion Project 070 | Other | Michigan | 2024-02-28 | 2025-09-27 | Behind | High | T002 | Task 002 of Airport Expansion Project 070 | In Progress | David | 21 | 0.11 | 4494 | 0 | 0
P070 | Airport Expansion Project 070 | Other | Florida | 2024-02-28 | 2024-04-01 | Behind | High | T003 | Task 003 of Airport Expansion Project 070 | Completed | Alice | 26 | 1 | 7738 | 7435 | 0.96084
P071 | Shopping Mall Renovation Project 071 | Renovation | Virginia | 2024-02-10 | 2024-02-18 | On Track | High | T001 | Task 001 of Shopping Mall Renovation Project 071 | Completed | Eve | 32 | 1 | 8568 | 8546 | 0.99743
P071 | Shopping Mall Renovation Project 071 | Renovation | Texas | 2024-02-10 | 2024-02-19 | On Track | High | T002 | Task 002 of Shopping Mall Renovation Project 071 | In Progress | Eve | 3 | 0.62 | 1052 | 0 | 0
P071 | Shopping Mall Renovation Project 071 | Renovation | Pennsylvania | 2024-02-10 | 2024-02-17 | On Track | High | T003 | Task 003 of Shopping Mall Renovation Project 071 | Completed | Alice | 10 | 1 | 7325 | 6853 | 0.93556
P072 | University Dormitory Construction Project 072 | Construction | Ohio | 2024-04-23 | 2025-05-27 | On Hold | High | T001 | Task 001 of University Dormitory Construction Project 072 | In Progress | Frank | 20 | 0.77 | 7862 | 0 | 0
P072 | University Dormitory Construction Project 072 | Construction | Georgia | 2024-04-23 | 2024-05-26 | On Hold | High | T002 | Task 002 of University Dormitory Construction Project 072 | Completed | Bob | 29 | 1 | 7708 | 7268 | 0.94292
P072 | University Dormitory Construction Project 072 | Construction | New Jersey | 2024-04-23 | 2025-06-09 | On Hold | Medium | T003 | Task 003 of University Dormitory Construction Project 072 | Pending | Alice | 0 | 0.36 | 3260 | 0 | 0
P073 | Sports Stadium Upgrade Project 073 | Other | Texas | 2024-05-06 | 2024-09-23 | Behind | Low | T001 | Task 001 of Sports Stadium Upgrade Project 073 | Completed | Alice | 29 | 1 | 1702 | 1411 | 0.82902
P073 | Sports Stadium Upgrade Project 073 | Other | Virginia | 2024-05-06 | 2024-08-22 | Behind | High | T002 | Task 002 of Sports Stadium Upgrade Project 073 | Completed | Bob | 24 | 1 | 8403 | 8115 | 0.96573
P073 | Sports Stadium Upgrade Project 073 | Other | Texas | 2024-05-06 | 2024-09-14 | Behind | High | T003 | Task 003 of Sports Stadium Upgrade Project 073 | Completed | David | 14 | 1 | 4955 | 4586 | 0.92553
P074 | Public Library Renovation Project 074 | Renovation | New York | 2024-05-21 | 2024-07-26 | Behind | High | T001 | Task 001 of Public Library Renovation Project 074 | Pending | Grace | 13 | 0.74 | 3533 | 0 | 0
P074 | Public Library Renovation Project 074 | Renovation | Washington | 2024-05-21 | 2024-08-01 | Behind | High | T002 | Task 002 of Public Library Renovation Project 074 | Pending | Alice | 8 | 0.18 | 8279 | 0 | 0
P074 | Public Library Renovation Project 074 | Renovation | Texas | 2024-05-21 | 2024-07-17 | Behind | High | T003 | Task 003 of Public Library Renovation Project 074 | In Progress | Charlie | 39 | 0.05 | 3680 | 0 | 0
P075 | Building a Park Project 075 | Other | Texas | 2024-05-11 | 2024-06-13 | Behind | Medium | T001 | Task 001 of Building a Park Project 075 | Completed | Ivy | 11 | 1 | 8493 | 12398 | 1.4598
P075 | Building a Park Project 075 | Other | Washington | 2024-05-11 | 2025-09-12 | Behind | Medium | T002 | Task 002 of Building a Park Project 075 | Pending | Alice | 11 | 0.26 | 3828 | 0 | 0
P075 | Building a Park Project 075 | Other | Virginia | 2024-05-11 | 2025-07-26 | Behind | Medium | T003 | Task 003 of Building a Park Project 075 | In Progress | Bob | 0 | 0.29 | 6118 | 0 | 0
P076 | Renovation of a School Project 076 | Renovation | Michigan | 2024-07-11 | 2024-08-01 | On Track | High | T001 | Task 001 of Renovation of a School Project 076 | Pending | Bob | 15 | 0.71 | 6558 | 0 | 0
P076 | Renovation of a School Project 076 | Renovation | New York | 2024-07-11 | 2024-08-11 | On Track | Medium | T002 | Task 002 of Renovation of a School Project 076 | Completed | Eve | 19 | 1 | 1044 | 899 | 0.86111
P076 | Renovation of a School Project 076 | Renovation | Ohio | 2024-07-11 | 2024-08-01 | On Track | High | T003 | Task 003 of Renovation of a School Project 076 | Pending | Eve | 10 | 0.21 | 7397 | 0 | 0
P077 | Innovation of a Classroom Project 077 | Innovation | California | 2024-04-09 | 2025-02-07 | On Hold | Medium | T001 | Task 001 of Innovation of a Classroom Project 077 | In Progress | Eve | 2 | 0.85 | 8832 | 0 | 0
P077 | Innovation of a Classroom Project 077 | Innovation | Virginia | 2024-04-09 | 2024-05-12 | On Hold | High | T002 | Task 002 of Innovation of a Classroom Project 077 | Completed | Charlie | 39 | 1 | 3123 | 2841 | 0.9097
P077 | Innovation of a Classroom Project 077 | Innovation | Florida | 2024-04-09 | 2025-03-13 | On Hold | Low | T003 | Task 003 of Innovation of a Classroom Project 077 | Pending | David | 1 | 0.15 | 6854 | 0 | 0
P078 | Construction of a Hospital Wing Project 078 | Construction | Michigan | 2024-01-26 | 2024-04-19 | On Hold | High | T001 | Task 001 of Construction of a Hospital Wing Project 078 | Completed | Alice | 25 | 1 | 8429 | 8416 | 0.99846
P078 | Construction of a Hospital Wing Project 078 | Construction | New Jersey | 2024-01-26 | 2024-03-18 | On Hold | High | T002 | Task 002 of Construction of a Hospital Wing Project 078 | In Progress | Grace | 4 | 0.95 | 1501 | 0 | 0
P078 | Construction of a Hospital Wing Project 078 | Construction | Pennsylvania | 2024-01-26 | 2024-04-09 | On Hold | Medium | T003 | Task 003 of Construction of a Hospital Wing Project 078 | Completed | Alice | 12 | 1 | 8487 | 8486 | 0.99988
P079 | Road Expansion Project 079 | Infrastructure | California | 2024-04-22 | 2025-01-13 | Completed | High | T001 | Task 001 of Road Expansion Project 079 | In Progress | Grace | 13 | 0.11 | 6425 | 0 | 0
P079 | Road Expansion Project 079 | Infrastructure | Florida | 2024-04-22 | 2025-03-15 | Completed | High | T002 | Task 002 of Road Expansion Project 079 | In Progress | Ivy | 34 | 0.05 | 8044 | 0 | 0
P079 | Road Expansion Project 079 | Infrastructure | New York | 2024-04-22 | 2024-05-25 | Completed | Medium | T003 | Task 003 of Road Expansion Project 079 | Completed | Charlie | 13 | 1 | 9524 | 9474 | 0.99475
P080 | Bridge Maintenance Project 080 | Maintenance | Ohio | 2024-04-16 | 2024-07-09 | On Track | High | T001 | Task 001 of Bridge Maintenance Project 080 | Pending | Eve | 13 | 0.7 | 4368 | 0 | 0
P080 | Bridge Maintenance Project 080 | Maintenance | New Jersey | 2024-04-16 | 2024-06-23 | On Track | Low | T002 | Task 002 of Bridge Maintenance Project 080 | In Progress | Grace | 15 | 0.65 | 2261 | 0 | 0
P080 | Bridge Maintenance Project 080 | Maintenance | Texas | 2024-04-16 | 2024-07-06 | On Track | Medium | T003 | Task 003 of Bridge Maintenance Project 080 | Completed | Alice | 27 | 1 | 8706 | 8333 | 0.95716
P081 | Office Building Renovation Project 081 | Renovation | Pennsylvania | 2024-05-31 | 2025-01-04 | On Track | High | T001 | Task 001 of Office Building Renovation Project 081 | In Progress | Alice | 26 | 0.08 | 1149 | 0 | 0
P081 | Office Building Renovation Project 081 | Renovation | Virginia | 2024-05-31 | 2025-03-03 | On Track | Medium | T002 | Task 002 of Office Building Renovation Project 081 | In Progress | Frank | 5 | 0.09 | 5011 | 0 | 0
P081 | Office Building Renovation Project 081 | Renovation | North Carolina | 2024-05-31 | 2024-07-03 | On Track | High | T003 | Task 003 of Office Building Renovation Project 081 | Completed | Ivy | 5 | 1 | 6163 | 5756 | 0.93396
P082 | Apartment Complex Development Project 082 | Other | Ohio | 2024-07-01 | 2025-03-12 | On Track | Medium | T001 | Task 001 of Apartment Complex Development Project 082 | In Progress | Ivy | 4 | 0.47 | 7524 | 0 | 0
P082 | Apartment Complex Development Project 082 | Other | Florida | 2024-07-01 | 2024-09-25 | On Track | Medium | T002 | Task 002 of Apartment Complex Development Project 082 | Completed | Grace | 10 | 1 | 2202 | 1878 | 0.85286
P082 | Apartment Complex Development Project 082 | Other | Pennsylvania | 2024-07-01 | 2025-03-17 | On Track | High | T003 | Task 003 of Apartment Complex Development Project 082 | In Progress | Ivy | 21 | 0.58 | 6835 | 0 | 0
P083 | Commercial Center Construction Project 083 | Construction | Michigan | 2024-03-20 | 2024-06-05 | Behind | Medium | T001 | Task 001 of Commercial Center Construction Project 083 | Completed | Alice | 24 | 1 | 8645 | 8633 | 0.99861
P083 | Commercial Center Construction Project 083 | Construction | New York | 2024-03-20 | 2024-05-25 | Behind | High | T002 | Task 002 of Commercial Center Construction Project 083 | Completed | Charlie | 19 | 1 | 9360 | 9196 | 0.98248
P083 | Commercial Center Construction Project 083 | Construction | Georgia | 2024-03-20 | 2024-06-15 | Behind | High | T003 | Task 003 of Commercial Center Construction Project 083 | In Progress | Charlie | 28 | 0.37 | 2183 | 0 | 0
P084 | Highway Reconstruction Project 084 | Other | Georgia | 2024-06-09 | 2025-05-08 | On Hold | Low | T001 | Task 001 of Highway Reconstruction Project 084 | Pending | Charlie | 17 | 0.54 | 1713 | 0 | 0
P084 | Highway Reconstruction Project 084 | Other | North Carolina | 2024-06-09 | 2025-04-19 | On Hold | Medium | T002 | Task 002 of Highway Reconstruction Project 084 | In Progress | Ivy | 16 | 0.91 | 6400 | 0 | 0
P084 | Highway Reconstruction Project 084 | Other | North Carolina | 2024-06-09 | 2025-03-25 | On Hold | High | T003 | Task 003 of Highway Reconstruction Project 084 | Pending | Eve | 14 | 0.2 | 3319 | 0 | 0
P085 | Airport Expansion Project 085 | Other | Virginia | 2024-08-03 | 2024-11-18 | Completed | Low | T001 | Task 001 of Airport Expansion Project 085 | Pending | Alice | 17 | 0.02 | 8340 | 0 | 0
P085 | Airport Expansion Project 085 | Other | Illinois | 2024-08-03 | 2024-09-25 | Completed | High | T002 | Task 002 of Airport Expansion Project 085 | Completed | David | 15 | 1 | 4749 | 4572 | 0.96273
P085 | Airport Expansion Project 085 | Other | New Jersey | 2024-08-03 | 2024-11-19 | Completed | High | T003 | Task 003 of Airport Expansion Project 085 | Pending | Alice | 24 | 0.51 | 6222 | 0 | 0
P086 | Shopping Mall Renovation Project 086 | Renovation | Pennsylvania | 2024-01-29 | 2024-12-10 | Completed | High | T001 | Task 001 of Shopping Mall Renovation Project 086 | In Progress | Eve | 35 | 0.54 | 9246 | 0 | 0
P086 | Shopping Mall Renovation Project 086 | Renovation | Pennsylvania | 2024-01-29 | 2024-09-25 | Completed | High | T002 | Task 002 of Shopping Mall Renovation Project 086 | Completed | Eve | 6 | 1 | 7327 | 7120 | 0.97175
P086 | Shopping Mall Renovation Project 086 | Renovation | Virginia | 2024-01-29 | 2024-10-17 | Completed | High | T003 | Task 003 of Shopping Mall Renovation Project 086 | Pending | Alice | 19 | 0.25 | 6331 | 0 | 0
P087 | University Dormitory Construction Project 087 | Construction | California | 2024-02-17 | 2025-09-11 | On Track | High | T001 | Task 001 of University Dormitory Construction Project 087 | In Progress | Frank | 8 | 0.06 | 2256 | 0 | 0
P087 | University Dormitory Construction Project 087 | Construction | New York | 2024-02-17 | 2025-10-07 | On Track | Medium | T002 | Task 002 of University Dormitory Construction Project 087 | Pending | Bob | 1 | 0.45 | 5371 | 0 | 0
P087 | University Dormitory Construction Project 087 | Construction | North Carolina | 2024-02-17 | 2025-10-06 | On Track | High | T003 | Task 003 of University Dormitory Construction Project 087 | In Progress | Alice | 12 | 0.3 | 2434 | 0 | 0
P088 | Sports Stadium Upgrade Project 088 | Other | Georgia | 2024-07-21 | 2025-02-13 | Completed | High | T001 | Task 001 of Sports Stadium Upgrade Project 088 | In Progress | Alice | 16 | 0.29 | 7504 | 0 | 0
P088 | Sports Stadium Upgrade Project 088 | Other | Virginia | 2024-07-21 | 2025-02-02 | Completed | Medium | T002 | Task 002 of Sports Stadium Upgrade Project 088 | Pending | Bob | 30 | 0.48 | 7717 | 0 | 0
P088 | Sports Stadium Upgrade Project 088 | Other | Washington | 2024-07-21 | 2024-12-21 | Completed | High | T003 | Task 003 of Sports Stadium Upgrade Project 088 | In Progress | David | 18 | 0.77 | 4651 | 0 | 0
P089 | Public Library Renovation Project 089 | Renovation | Georgia | 2024-05-26 | 2025-05-06 | On Track | Medium | T001 | Task 001 of Public Library Renovation Project 089 | In Progress | Grace | 17 | 0.75 | 5791 | 0 | 0
P089 | Public Library Renovation Project 089 | Renovation | Washington | 2024-05-26 | 2025-07-18 | On Track | High | T002 | Task 002 of Public Library Renovation Project 089 | In Progress | Alice | 4 | 0.23 | 4133 | 0 | 0
P089 | Public Library Renovation Project 089 | Renovation | Washington | 2024-05-26 | 2024-06-28 | On Track | Medium | T003 | Task 003 of Public Library Renovation Project 089 | Completed | Charlie | 34 | 1 | 8716 | 8476 | 0.97246
P090 | Building a Park Project 090 | Other | Michigan | 2024-06-11 | 2024-07-14 | Completed | High | T001 | Task 001 of Building a Park Project 090 | Completed | Ivy | 21 | 1 | 9174 | 9031 | 0.98441
P090 | Building a Park Project 090 | Other | North Carolina | 2024-06-11 | 2025-09-01 | Completed | Low | T002 | Task 002 of Building a Park Project 090 | In Progress | Alice | 27 | 0.08 | 9702 | 0 | 0
P090 | Building a Park Project 090 | Other | Georgia | 2024-06-11 | 2025-10-21 | Completed | High | T003 | Task 003 of Building a Park Project 090 | In Progress | Bob | 21 | 0.96 | 8975 | 0 | 0
P091 | Renovation of a School Project 091 | Renovation | Michigan | 2024-05-22 | 2024-06-24 | On Hold | High | T001 | Task 001 of Renovation of a School Project 091 | Completed | Bob | 23 | 1 | 7491 | 7138 | 0.95288
P091 | Renovation of a School Project 091 | Renovation | Michigan | 2024-05-22 | 2025-03-13 | On Hold | Medium | T002 | Task 002 of Renovation of a School Project 091 | Pending | Eve | 22 | 0.92 | 4013 | 0 | 0
P091 | Renovation of a School Project 091 | Renovation | New York | 2024-05-22 | 2025-03-21 | On Hold | Low | T003 | Task 003 of Renovation of a School Project 091 | Pending | Eve | 33 | 0.64 | 1670 | 0 | 0
P092 | Innovation of a Classroom Project 092 | Innovation | California | 2024-03-03 | 2024-11-26 | Completed | Medium | T001 | Task 001 of Innovation of a Classroom Project 092 | Pending | Eve | 22 | 0.04 | 6004 | 0 | 0
P092 | Innovation of a Classroom Project 092 | Innovation | Illinois | 2024-03-03 | 2024-09-25 | Completed | Medium | T002 | Task 002 of Innovation of a Classroom Project 092 | Completed | Charlie | 13 | 1 | 9649 | 9485 | 0.983
P092 | Innovation of a Classroom Project 092 | Innovation | Georgia | 2024-03-03 | 2024-09-25 | Completed | High | T003 | Task 003 of Innovation of a Classroom Project 092 | Completed | David | 11 | 1 | 5921 | 5788 | 0.97754
P093 | Construction of a Hospital Wing Project 093 | Construction | Virginia | 2024-08-19 | 2024-09-21 | Completed | Low | T001 | Task 001 of Construction of a Hospital Wing Project 093 | Completed | Alice | 40 | 1 | 4306 | 3888 | 0.90293
P093 | Construction of a Hospital Wing Project 093 | Construction | Illinois | 2024-08-19 | 2025-04-19 | Completed | Low | T002 | Task 002 of Construction of a Hospital Wing Project 093 | In Progress | Grace | 31 | 0.75 | 8367 | 0 | 0
P093 | Construction of a Hospital Wing Project 093 | Construction | Georgia | 2024-08-19 | 2024-09-21 | Completed | Low | T003 | Task 003 of Construction of a Hospital Wing Project 093 | Completed | Charlie | 0 | 1 | 4178 | 4148 | 0.99282
P094 | Road Expansion Project 094 | Infrastructure | North Carolina | 2024-06-28 | 2024-10-06 | Behind | High | T001 | Task 001 of Road Expansion Project 094 | In Progress | Grace | 13 | 0.44 | 1773 | 0 | 0
P094 | Road Expansion Project 094 | Infrastructure | Illinois | 2024-06-28 | 2024-09-29 | Behind | High | T002 | Task 002 of Road Expansion Project 094 | In Progress | Ivy | 20 | 0.42 | 7829 | 0 | 0
P094 | Road Expansion Project 094 | Infrastructure | Virginia | 2024-06-28 | 2024-09-23 | Behind | Medium | T003 | Task 003 of Road Expansion Project 094 | In Progress | Charlie | 39 | 0.37 | 1447 | 3357 | 2.32
P095 | Bridge Maintenance Project 095 | Maintenance | Ohio | 2024-02-17 | 2024-08-02 | Behind | Medium | T001 | Task 001 of Bridge Maintenance Project 095 | Pending | Eve | 24 | 0.81 | 8329 | 0 | 0
P095 | Bridge Maintenance Project 095 | Maintenance | Illinois | 2024-02-17 | 2024-06-29 | Behind | Low | T002 | Task 002 of Bridge Maintenance Project 095 | In Progress | Grace | 34 | 0.97 | 6160 | 0 | 0
P095 | Bridge Maintenance Project 095 | Maintenance | New Jersey | 2024-02-17 | 2024-07-27 | Behind | High | T003 | Task 003 of Bridge Maintenance Project 095 | In Progress | Charlie | 7 | 0.58 | 6083 | 0 | 0
P096 | Office Building Renovation Project 096 | Renovation | Georgia | 2024-03-03 | 2025-05-06 | On Track | Low | T001 | Task 001 of Office Building Renovation Project 096 | Pending | Alice | 17 | 0.69 | 1235 | 0 | 0
P096 | Office Building Renovation Project 096 | Renovation | Illinois | 2024-03-03 | 2025-01-05 | On Track | Medium | T002 | Task 002 of Office Building Renovation Project 096 | In Progress | Frank | 20 | 0.08 | 2984 | 6060 | 2.0308
P096 | Office Building Renovation Project 096 | Renovation | Ohio | 2024-03-03 | 2025-03-09 | On Track | High | T003 | Task 003 of Office Building Renovation Project 096 | Pending | Ivy | 32 | 0.92 | 5211 | 0 | 0
P097 | Apartment Complex Development Project 097 | Other | Washington | 2024-06-08 | 2024-12-08 | Behind | High | T001 | Task 001 of Apartment Complex Development Project 097 | Pending | Ivy | 9 | 0.5 | 6292 | 0 | 0
P097 | Apartment Complex Development Project 097 | Other | Florida | 2024-06-08 | 2025-03-08 | Behind | Medium | T002 | Task 002 of Apartment Complex Development Project 097 | Pending | Grace | 17 | 0.2 | 2335 | 0 | 0
P097 | Apartment Complex Development Project 097 | Other | Virginia | 2024-06-08 | 2024-12-21 | Behind | High | T003 | Task 003 of Apartment Complex Development Project 097 | Pending | Ivy | 32 | 0.66 | 3956 | 0 | 0
P098 | Commercial Center Construction Project 098 | Construction | Illinois | 2024-08-15 | 2025-01-23 | Completed | Medium | T001 | Task 001 of Commercial Center Construction Project 098 | In Progress | Alice | 12 | 0.67 | 8906 | 0 | 0
P098 | Commercial Center Construction Project 098 | Construction | Texas | 2024-08-15 | 2025-01-28 | Completed | Medium | T002 | Task 002 of Commercial Center Construction Project 098 | Pending | Charlie | 25 | 0.83 | 8346 | 0 | 0
P098 | Commercial Center Construction Project 098 | Construction | Michigan | 2024-08-15 | 2025-04-27 | Completed | High | T003 | Task 003 of Commercial Center Construction Project 098 | In Progress | Charlie | 20 | 0.3 | 5134 | 0 | 0
P099 | Highway Reconstruction Project 099 | Other | New Jersey | 2024-05-31 | 2024-12-22 | Completed | Medium | T001 | Task 001 of Highway Reconstruction Project 099 | Pending | Charlie | 7 | 0.14 | 7307 | 0 | 0
P099 | Highway Reconstruction Project 099 | Other | New York | 2024-05-31 | 2025-03-01 | Completed | High | T002 | Task 002 of Highway Reconstruction Project 099 | Pending | Ivy | 5 | 0.36 | 9425 | 0 | 0
P099 | Highway Reconstruction Project 099 | Other | Florida | 2024-05-31 | 2025-03-11 | Completed | High | T003 | Task 003 of Highway Reconstruction Project 099 | Pending | Eve | 19 | 0.91 | 5199 | 0 | 0
P100 | Airport Expansion Project 100 | Other | Virginia | 2024-08-08 | 2024-09-02 | On Track | Medium | T001 | Task 001 of Airport Expansion Project 100 | Pending | Charlie | 30 | 0.85 | 2156 | 0 | 0
P100 | Airport Expansion Project 100 | Other | Pennsylvania | 2024-08-08 | 2024-08-30 | On Track | Medium | T002 | Task 002 of Airport Expansion Project 100 | Pending | David | 12 | 0.02 | 1502 | 0 | 0
P100 | Airport Expansion Project 100 | Other | Virginia | 2024-08-08 | 2024-08-30 | On Track | Medium | T003 | Task 003 of Airport Expansion Project 100 | In Progress | Alice | 38 | 0.86 | 8619 | 0 | 0

## ANALYSIS
[6 empty] | PROJECT ANALYSIS BREAKDOWN |  |  | TASK ANALYSIS
Count of Project ID |  | Count of Task ID |  |  |  | PROJECTS | 54 |  | TASK | 54
54 |  | 54 |  |  |  | BUDGET | 336554 |  | COMPLETED | 87
[6 empty] | COST | 100465 |  | HOURS SPENT | 5763
Sum of Budget | Sum of Actual Cost | Sum of Hours Spent |  |  |  | BUDGET UTILIZED | 29.85% |  | COMPLETION RATE | 161.1%
336554 | 100465 | 5763
PROJECT BY TYPE |  |  |  | PROJECT BY PRIOPRITY
Row Labels | Count of Project ID |  |  | Row Labels | Count of Project ID
Maintenance | 2 |  |  | High | 27
Innovation | 2 |  |  | Low | 11
Construction | 16 |  |  | Medium | 16
Renovation | 16 |  |  | Grand Total | 54
Other | 18
Grand Total | 54
PROJECT BY STATUS
Row Labels | Count of Project ID | STATUS | PROJECT | PROJECT BY LOCATION
On Hold | 11 | On Hold | 11 | Row Labels | Count of Project ID |  | STATE | Project
Completed | 13 | Completed | 13 | California | 6 |  | California | 6
Behind | 15 | Behind | 15 | Florida | 4 |  | Florida | 4
On Track | 15 | On Track | 15 | Georgia | 6 |  | Georgia | 6
Grand Total | 54 |  |  | Illinois | 2 |  | Illinois | 2
|  |  |  | Michigan | 5 |  | Michigan | 5
PROJECT BUDGET & EXPENSES OVER TIME |  |  |  | New Jersey | 4 |  | New Jersey | 4
Row Labels | Sum of Budget | Sum of Actual Cost |  | New York | 2 |  | New York | 2
Jan | 267344 | 80477 |  | North Carolina | 4 |  | North Carolina | 4
Feb | 166966 | 54532 |  | Ohio | 3 |  | Ohio | 3
Mar | 155876 | 80206 |  | Pennsylvania | 4 |  | Pennsylvania | 4
Apr | 213038 | 52009 |  | Texas | 5 |  | Texas | 5
May | 223592 | 76867 |  | Virginia | 5 |  | Virginia | 5
Jun | 278028 | 82083 |  | Washington | 4 |  | Washington | 4
Jul | 232082 | 58311 |  | Grand Total | 54
Aug | 150354 | 33936
Grand Total | 1687280 | 518421
|  |  |  | Task Status | Completed
Row Labels | Count of Task ID
Completed | 14 | 14 |  | Row Labels | Count of Task ID | Months | task | task
In Progress | 21 |  |  | Feb | 1 | Feb | 1 | 1
Pending | 19 |  |  | Apr | 3 | Apr | 3 | 3
Grand Total | 54 |  |  | Jun | 1 | Jun | 1 | 1
|  |  |  | Jul | 3 | Jul | 3 | 3
TASK BY STATUS |  |  |  | Aug | 2 | Aug | 2 | 2
Row Labels | Count of Task ID |  |  | Sep | 4 | Sep | 4 | 4
Completed | 14 |  |  | Grand Total | 14 | Grand Total | 14 | 14
In Progress | 21 |  |  |  |  | 0 | 0 | 0
Pending | 19
Grand Total | 54
HOURS SPENT by Task
Row Labels | Sum of Hours Spent
T001 | 505 |  |  | Count of Task ID | Column Labels
T002 | 105 |  |  | Row Labels | Completed | In Progress | Pending | Grand Total
T003 | 450 |  |  | Jan |  | 3 | 1 | 4
Grand Total | 1060 |  |  | Feb | 1 | 1 |  | 2
|  |  |  | Mar |  | 2 | 1 | 3
Progress by Task |  |  |  | Apr | 3 |  | 1 | 4
Row Labels | Sum of Progress |  |  | May |  |  | 3 | 3
T001 | 16.03 |  |  | Jun | 1 | 2 | 3 | 6
T002 | 3.45 |  |  | Jul | 3 | 3 |  | 6
T003 | 12.75 |  |  | Aug | 2 | 1 | 3 | 6
Grand Total | 32.23 |  |  | Sep | 4 | 2 | 3 | 9
|  |  |  | Oct |  | 2 | 1 | 3
|  |  |  | Nov |  | 3 | 2 | 5
|  |  |  | Dec |  | 2 | 1 | 3
|  |  |  | Grand Total | 14 | 21 | 19 | 54

## PROJECT SUMMARY
Projects | Budget | Cost | Budget Utilisation
54 | 336554 | 100465 | 29.85%
s
This chart isn’t available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
PROJECT MANAGEMENT SUMMARY
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## TASK SUMMARY
Task | Completed | Hours Spent | Completion Rate
54 | 87 | 5763 | 161.1%
TASK SUMMARY
Progress by Task Id & Hours Spent
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.